## Project schedule
| 화장품 사용 주기 및 평가 관리 앱 |  |  |  |  | Project start: | [7 empty] | 2025-05-19
| 주혜진 |  |  |  |  | Display week: | [7 empty] | 1
[6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30
| TASK | PROGRESS | START | END | time axis 2025-05-19 to 2025-07-06
 | time axis 2025-05-19 to 2025-07-06
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
1. 아이디어 구체화 및 계획 수립
| 앱의 목적과 주요 기능 정의 | 100% | 2025-05-19 | 2025-05-19 | 1
| 타겟 사용자 및 시장 조사 | 100% | 2025-05-19 | 2025-05-19 | 1
| 프로젝트 목표 설정 및 초안 작성 | 100% | 2025-05-19 | 2025-05-19 | 1
2. 기획 및 설계
| 기능 목록 확정 (요구사항 정의서) | 100% | 2025-05-19 | 2025-05-20 | 2
| 앱 정보 구조(IA) 및 사용자 흐름(User case diagram) 작성 | 50% | 2025-05-21 | 2025-05-22 | 2
| 와이어프레임 제작 | 0% | 2025-05-23 | 2025-05-25 | 3 | bar: 2025-05-25
| 플레이스토어 페이지 정보 구상 | 0% | 2025-05-26 | 2025-05-26 | 1
3. 개발 환경 설정
| 개발 플랫폼 결정 | 0% | 2025-05-26 | 2025-05-26 | 1
| 필요한 툴 및 라이브러리 세팅 | 0% | 2025-05-26 | 2025-05-26 | 1
| 로컬 데이터 저장소 선정 | 0% | 2025-05-26 | 2025-05-26 | 1
| 버전 관리 시스템 설정 | 0% | 2025-05-26 | 2025-05-26 | 1
4. 기능 개발
| View 레이아웃 7개 (약 21시간 소요) | 0% | 2025-05-27 | 2025-06-02 | bar: 2025-06-02
| 화장품 등록 (요구사항 4개, 9.5시간) |  | 2025-06-03 | 2025-06-06
| 등록한 화장품 목록 보기 (요구사항 3개, 5.5시간) | 0% | 2025-06-07 | 2025-06-09
| 화장품 사용 체크 (요구사항 3개, 6시간) | 0% | 2025-06-10 | 2025-06-11
| 대시보드 (요구사항 2개, 3.5시간) | 0% | 2025-06-12 | 2025-06-13
| 푸시 알림 (요구사항 2개, 3시간) | 0% | 2025-06-14 | 2025-06-15
| 사용 평가 (요구사항 2개, 4.5시간) | 0% | 2025-06-16 | 2025-06-16 | 1 | bar: 2025-06-16
5. 테스트
| 실제 안드로이드 기기에서 테스트 | 0% | 2025-06-17 | 2025-06-17 | 1
| 사용자 피드백 수집 | 0% | 2025-06-18 | 2025-06-18 | 1
| 동작/디자인 개선 사항 정리 | 0% | 2025-06-19 | 2025-06-19 | 1
6. 디버깅 및 수정
| 발견된 오류 및 버그 수정 | 0% | 2025-06-20 | 2025-06-20 | 1
| 성능 최적화 | 0% | 2025-06-21 | 2025-06-22 | 2
| 디자인 및 기능 피드백 반영 | 0% | 2025-06-22 | 2025-06-23 | 2 | bar: 2025-06-23
7. 배포 준비
| 앱 아이콘, 스플래시 화면 추가 | 0% | 2025-06-24 | 2025-06-24 | 1
ㅑ | 개인정보 처리방침 작성 (플레이스토어 요구사항) | 0% | 2025-06-25 | 2025-06-25 | 1
| 앱 번들(.aab) 빌드 | 0% | 2025-06-26 | 2025-06-26 | 1
| 플레이콘솔에 앱 등록 | 0% | 2025-06-27 | 2025-06-27 | 1
| 앱 설명, 스크린샷, 정책 문서 업로드 | 0% | 2025-06-27 | 2025-06-27 | 1
| 내부 테스트 트랙 업로드 및 테스트 | 0% | 2025-06-27 | 2025-07-06 | 10 | bar: 2025-06-27
Insert new rows ABOVE this one